## Group7_EstimatedEffort
Simply CDL | [6 empty] | Brian | Noor | Paul | Zach
|  |  | Role | Owner | Estimated by Task | Actual by Task | Actual by Task | Actual by Task | Actual by Task | Actual by Task
Preliminary & Parallel Tasks
| Architecture |  |  |  | 12 | 5
|  | Design architecture | Project Manager | Paul | 12 | 5 | 1 | 1 | 1 | 2
| Requirements |  |  |  | 9 | 11
|  | Gather | Requirements Engineer | Paul, Zach | 2 | 5 | 1 |  | 2 | 2
|  | Analyze | Requirements Engineer | Paul, Zach | 4 | 4 | 1 | 1 | 1 | 1
|  | Specify | Requirements Engineer | Paul, Zach | 3 | 2 |  |  |  | 2
| Documentation |  |  |  | 28 | 6
|  | Project Charter | Project Manager | Paul, Zach | 2 | 0
|  | Release Plan | Project Manager | Paul, Zach | 2 | 1 |  |  |  | 1
|  | Requirements Document | Project Manager, Requirements Engineer | Paul, Zach | 5 | 4 | 1 |  | 1 | 2
|  | Project Plan | Project Manager, Developers | Brian, Noor, Paul, Zach | 5 | 1 |  |  |  | 1
|  | Architecture Document | Architect | Brian, Noor | 4 | 0
|  | Test Report | Tester | Noor, Brian | 8 | 0
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Brian, Noor, Paul, Zach | 2 | 0
Iteration 1:
| Development |  |  |  | 34 | 19.75
|  | Determine technology needs | Developers | Brian, Noor, Paul, Zach | 1 | 1 |  |  |  | 1
|  | Research and learn new language and environment: HTML, CSS, PHP, SQL | Developers | Brian, Noor, Paul, Zach | 20 | 7.25 | 1 | 1 | 1 | 4.25
|  | Set up development server software | Developers | Brian, Noor, Paul, Zach | 3 | 5 | 2 |  |  | 3
|  | Create and implement source control (GitHub) | Developers | Brian, Noor, Paul, Zach | 2 | 2 |  |  | 1 | 1
|  | Unit testing | Developers | Brian, Noor, Paul, Zach | 2 | 0
|  | Site map | Developers | Brian, Noor, Paul, Zach | 3 | 1.5 |  |  | 1.5
|  | WordPress Installation | Developers | Brian, Noor, Paul, Zach | 1 | 2 | 1 |  |  | 1
|  | Website Structure | Developers | Brian, Noor, Paul, Zach | 2 | 1 |  |  |  | 1
Iteration 2:
| Development |  |  |  | 25.5 | 17.25
|  | Remove "Powered by WordPress" | Developers | Zach | 0.5 | 1 |  |  | 0.75 | 0.25
|  | SEO Plugin installed & configured | Developers | Zach | 1 | 1 |  |  |  | 1
|  | Work with client to create content | Developers | Paul, Brian | 2 | 0
|  | Site prototype | Developers | Zach, Brian | 2 | 4 | 1 |  | 1 | 2
|  | Create content | Developers | Brian, Noor, Paul | --- | --- |  |  | 1
|  | Homepage | Developers | Brian, Noor, Paul | 3 | 0
|  | About | Developers | Brian, Noor, Paul | 2 | 1 | 1
|  | Services | Developers | Brian, Noor, Paul | 2 | 1 | 1
|  | Other Pages | Developers | Brian, Noor, Paul | 2 | 0
|  | History/Mission Statement/Values | Developers | Brian, Noor, Paul | 1 | 1 |  |  | 1
|  | Any remaining content | Developers | Brian, Noor, Paul | 2 | 0
|  | Update content to be more engaging/compelling | Developers | Noor, Paul | 1 | 1 |  | 0.25 | 0.75
|  | Modify content for SEO purposes | Developers | Noor, Zach | 2 | 0
|  | Contact us form | Developers | Zach | 1 | 1 |  |  |  | 1
|  | Install job application forms | Developers | Zach, Brian | 4 | 6.25 |  |  | 0.25 | 6
Iteration 3:
| Development |  |  |  | 24 | 5.25
|  | Color scheme | Developers | Zach | 2 | 1 |  |  |  | 1
|  | Responsiveness test | Developers | Brian | 1 | 0.5 | 0.5
|  | Test multiple device types | Developers | Brian | 1 | 0.5 | 0.5
|  | Photographs | Developers | Brian, Noor, Paul, Zach | 2 | 0.25 |  |  | 0.25
|  | Final polish | Developers | Brian, Noor, Paul, Zach | 4 | 0
|  | Refactor absolutely anything | Developers | Brian, Noor, Paul, Zach | 5 | 1 |  |  | 1
|  | Finalize content | Developers | Brian, Noor, Paul, Zach | 5 | 1 |  |  |  | 1
|  | Meet with client to discuss finishing details | Developers | Brian, Noor, Paul, Zach | 3 | 0
|  | Deliver IP to client | Developers | Brian, Noor, Paul, Zach | 1 | 1 |  |  |  | 1
Total |  |  |  |  | 132.5 | 64.25 | 12 | 3.25 | 14.5 | 35.5